## Task Details
Task | Description | Start Date | End Date
Problem & Solution Statement | Define the problem your business solves and how your solution addresses it. | 2024-11-17 | 2024-11-24
Competitor Analysis | Research competitors to understand their products, pricing, and strategies. | 2024-12-10 | 2024-12-10
Survey Development | Design and finalize survey questions to gather insights on demand and barriers. | 2024-12-12 | 2024-12-12
Secondary Research | Gather industry trends, market data, and substitute product analysis.
Survey Distribution & Data Collection | Distribute surveys on platforms like MTurk and collect responses.
Customer Interviews | Conduct interviews with target customers to validate features and pricing.
Observation Study | Visit markets and expos to observe customer behavior and preferences.
Prototype Feedback | Create a visual prototype and gather feedback from focus groups.
Initial Data Analysis | Analyze survey and interview data to identify key insights.
Deliverable Preparation | Prepare presentations and reports summarizing your findings.

## Problem & Solution
Problem Statement
Many people struggle to get fresh, affordable produce year-round. Traditional farming methods can be expensive, waste resources, and depend on seasonal conditions. Urban and rural communities, as well as small businesses, often don’t have an easy or cost-effective way to grow their own food.
Solution Statement
Cameron County Containers turns shipping containers into hydroponic farms that grow food all year long. These systems are energy-efficient, use less water, and are easy to customize for different needs. They’re perfect for home gardeners, farmers, and small businesses looking for a sustainable way to grow fresh produce.

## Survey Development
Have you ever grown your own produce?
Have you heard of hydroponic farming?
How concerned are you about the following factors when considering a hydroponic farming system?
How important is sustainability to you when it comes to food production?
How often do you experience difficulty accessing fresh produce?
If you were to invest in a hydroponic farming system, what would your primary reason be?
What is your biggest concern about using a hydroponic farming system?
Where do you currently source most of your fresh produce?
Which feature would make a hydroponic system most appealing to you?
Would you consider growing your own produce using a sustainable method like hydroponics?